## Slide 1
PromptForge MVP
Foundation & Setup Phase: Establishing Infrastructure for Production-Ready Development
Duration:
2 weeks (10 working days)
Team:
3 core members
Effort:
94 story points
Budget:
$40,000

## Slide 2
Foundation & Setup Phase: Building the Backbone
2 weeks
Duration
3
Team Members
94
Story Points
$40K
Budget
Objective
Establish complete development infrastructure, tooling, and architectural foundations that enable rapid, high-quality development in subsequent phases.
Impact
Success in this phase directly impacts the velocity and quality of all downstream development work. This phase removes infrastructure as a blocker for the entire project.
Outcome
Phase completion enables Phase 2 (Core Platform Development) to begin immediately with zero infrastructure blockers.

## Slide 3
Week 1: Infrastructure Setup Delivers Foundation
39
Story Points
2
Team Members
5
Days
1
GitHub Repositories
3 fully configured repositories (backend, frontend, mobile) with branch protection and team access
2
CI/CD Pipeline
Automated testing, linting, and deployment workflows via GitHub Actions
3
AWS Infrastructure
RDS PostgreSQL, ElastiCache Redis, S3 storage, and Lambda functions across dev/staging/prod
4
Monitoring & Logging
Sentry error tracking, New Relic APM, CloudWatch logging with dashboards and alerts
5
Development Guide
Comprehensive setup documentation enabling all team members to begin development immediately
Week 1 completion enables Week 2 backend development and removes infrastructure as a blocker
✓ Ready for Phase 2

## Slide 4
Week 1 Task Breakdown: Five Critical Initiatives
Detailed allocation of infrastructure setup tasks with story points, assignees, and timeline
Task
Story Points
Assignee
Due Date
Status
Initialize GitHub Repositories
5
Engineering Lead
Day 1
Planned
Set Up GitHub Actions CI/CD
8
DevOps Engineer
Day 2
Planned
Configure AWS Infrastructure
13
DevOps Engineer
Day 3
Planned
Set Up Monitoring & Logging
8
DevOps Engineer
Day 4
Planned
Create Dev Environment Guide
5
Engineering Lead
Day 5
Planned
Week 1 Total
39
2 people
Day 5
Ready
Key Dependencies
None (Week 1 is foundational)
Team Utilization
39 SP ÷ 2 people = 19.5 SP/person
Impact
Enables Week 2 backend development

## Slide 5
Week 2: Backend Architecture Enables Core Platform
47
Story Points
2
Team Members
5
Days
1
Express Backend
Production-ready Node.js/Express application with TypeScript, proper project structure, and middleware
2
Database Schema
8 core tables with relationships, indexes, constraints, and migration system
3
Authentication System
JWT tokens, OAuth 2.0 integration (Google, GitHub), password management, and security measures
4
API Gateway
Express router with versioning, middleware stack (logging, validation, rate limiting, CORS), and standardized response formats
5
Core Services
User, Project, and Pack services with CRUD operations and business logic scaffolding
Week 2 completion enables Week 3 core platform development with zero infrastructure blockers
✓ Ready for Phase 2

## Slide 6
Week 2 Tasks: Five Backend Architecture Initiatives
Task ID
Task Name
Story Points
Assignee
Due Date
PFORGE-201
Set Up Express Backend
8
Backend Lead
Day 6
PFORGE-202
Create Database Schema
13
Backend Lead
Day 7
PFORGE-203
Implement JWT & OAuth
10
Backend Lead
Day 8
PFORGE-204
Create API Gateway & Middleware
8
Backend Lead
Day 9
PFORGE-205
Create Core Services
8
Backend Lead
Day 10
Week 2 Total:
47 story points | 2 people | Day 10
Key Dependencies:
Week 1 infrastructure must be complete
Week 2 Effort
47 SP
story points
Backend Implementation Process

## Slide 7
Team Structure: Focused Expertise for Foundation Phase
Engineering Lead
50%
Allocation
Key Responsibilities
GitHub repository setup and configuration
Development environment documentation
Architecture review and decisions
Technical leadership and mentoring
•
•
•
•
DevOps Engineer
100%
Allocation
Key Responsibilities
AWS infrastructure setup and configuration
CI/CD pipeline implementation
Monitoring and logging configuration
Infrastructure documentation and runbooks
•
•
•
•
Backend Lead
100%
Allocation (Week 2)
Key Responsibilities
Backend architecture and design
Database schema design and implementation
Authentication system implementation
API gateway and core services setup
•
•
•
•
Total FTE
3.0
FTE-Days
60
Utilization Rate
1.57 SP/FTE-day

## Slide 8
Total Budget
Budget Breakdown: $40,000
Personnel Costs
80%
Engineering Lead (50%):
$7,500
DevOps Engineer (100%):
$12,000
Backend Lead (100%, Week 2):
$12,500
Subtotal:
$32,000
Infrastructure & Services
12.5%
AWS setup & initial costs:
$3,000
Tools & monitoring services:
$2,000
Contingency
7.5%
Buffer for unexpected costs:
$3,000
Cost per Story Point:
$426
Cost per FTE-day:
$667

## Slide 9
Success Metrics: Clear Success Criteria
Infrastructure
✓
All GitHub repos created with branch protection
✓
CI/CD pipeline passing all checks
✓
AWS infrastructure operational across all environments
✓
Monitoring dashboards live with 0 critical alerts
Development
✓
Backend server running locally for all team members
✓
Database schema complete with 8 tables
✓
Auth endpoints functional (register, login, OAuth)
✓
API gateway responding <500ms latency
Team
✓
All developers can clone, build, and run locally
✓
Dev environment setup time <30 minutes
✓
Zero critical bugs in infrastructure
✓
100% of planned story points completed
Quality
✓
Code coverage 80%+ on backend
✓
Zero critical security vulnerabilities
✓
All tests passing (unit, integration)
✓
Documentation complete and reviewed
Phase Completion
16 of 16 Criteria Met
Ready for Phase 2
✓ Yes
Infrastructure Blockers
0 Remaining

## Slide 10
Risk Assessment: Mitigation Strategy
Identified risks with probability, impact, mitigation strategies, and contingency plans
Risk
Probability
Impact
Mitigation Strategy
Contingency Plan
AWS Setup Delays
Medium
High
Early planning with AWS team, use Infrastructure as Code (Terraform), pre-approved budget, dedicated DevOps engineer
Use alternative cloud provider (Azure/GCP), simplify initial infrastructure
CI/CD Complexity
Low
Medium
Use GitHub Actions templates, start with simple pipeline, iterate incrementally, documentation
Simplify pipeline initially, add complexity after Week 1
Database Design Issues
Low
High
Early schema review with team, documentation, design patterns, peer review before implementation
Redesign during Week 2, use migration scripts for changes
Team Onboarding
Low
Medium
Comprehensive setup guide, pair programming, mentoring, clear documentation, daily standups
Extend onboarding period, pair programming with experienced developers
Scope Creep
Medium
Medium
Strict scope adherence, clear JIRA tickets, weekly scope review, stakeholder communication
Cut non-essential features, defer to Phase 2, adjust timeline
Risk Mitigation Strategy
Daily standups to identify blockers early • Weekly risk review with stakeholders • Clear escalation path for critical issues • Pre-planned contingency tasks if ahead of schedule
Escalation Path
Technical blockers → Engineering Lead | Infrastructure issues → DevOps Engineer | Budget/timeline concerns → Product Manager | Critical issues → Executive team

## Slide 11
Timeline: 10-Day Execution Plan with Clear Milestones
Week 1: Infrastructure Setup
1
Day 1 - Monday
GitHub repositories initialized and team access configured
2
Day 2 - Tuesday
CI/CD pipeline operational and passing initial tests
3
Day 3 - Wednesday
AWS infrastructure live and accessible across environments
4
Day 4 - Thursday
Monitoring dashboards visible and alerting configured
5
Day 5 - Friday
Development environment guide completed and tested
Week 2: Backend Architecture
6
Day 6 - Monday
Express backend running locally with health check endpoint
7
Day 7 - Tuesday
Database schema complete with migrations and seed data
8
Day 8 - Wednesday
Auth endpoints working (register, login, OAuth)
9
Day 9 - Thursday
API gateway configured with middleware and rate limiting
10
Day 10 - Friday
Core services functional with CRUD operations
Scaling & Growth Path
Phase Completion
End of Day 10 (Friday, Week 2)
Ready for Phase 2
Monday, Week 3
Key Milestone
Zero infrastructure blockers for core platform development

## Slide 12
Handoff: Ready for Phase 2
Infrastructure Ready
Phase 1 Complete
✓
GitHub repositories with branch protection enabled
✓
CI/CD pipeline passing all checks (tests, linting, builds)
✓
AWS infrastructure operational across dev/staging/prod
✓
Monitoring dashboards live with 0 critical alerts
✓
Development environment setup guide completed
Backend Ready
Phase 1 Complete
✓
Express backend running locally with health check endpoint
✓
PostgreSQL database operational with 8 core tables
✓
Auth endpoints functional (register, login, OAuth)
✓
API gateway configured with middleware and rate limiting
✓
Core services functional with CRUD operations
Team Ready
Phase 1 Complete
✓
All developers can clone, build, and run locally
✓
Development workflow established and documented
✓
Code review process in place (2 reviewers required)
✓
Monitoring and alerting configured and operational
✓
Team trained on development environment and tools
Phase 2 Start Date
Monday, Week 3 Core Platform Development begins immediately with zero infrastructure blockers
Phase 2 Deliverables
Pack Service, Execution Engine, Composer Engine, Credits & Billing, Visualisation Service, and User & Project Service implementation

## Slide 13
Quality Assurance: Standards Embedded
Testing Approach
✓
Unit tests for all core services and utilities
✓
Integration tests for API endpoints and workflows
✓
End-to-end tests for user workflows
✓
Performance testing and load testing
Code Quality Standards
✓
ESLint + Prettier for consistent code formatting
✓
TypeScript strict mode for type safety
✓
Code review process with 2 required approvals
✓
Security scanning with Snyk and OWASP checks
Documentation Requirements
✓
API documentation with OpenAPI/Swagger specs
✓
Development setup guide and runbooks
✓
Architecture decision records (ADRs)
Quality Drives Growth
QA Impact
50% fewer bugs in production
Team Velocity
30% faster feature delivery
User Satisfaction
95%+ uptime guaranteed

## Slide 14
Communication Plan: Transparent Updates
Stakeholder communication cadence ensuring visibility and alignment throughout the phase
📅
Daily Standups
Time & Format
9:00 AM UTC — 15m, Zoom
Attendees
Eng Lead, Backend, DevOps, Frontend
Content
Completed tasks, blockers, today's plan
📊
Weekly Updates
Time & Format
Fri 4:00 PM UTC — 30m, Zoom + Slides
Attendees
PM, Eng Lead, CTO, Stakeholders
Content
Week summary, metrics, risks, next plan
🎯
Monthly Reviews
Time & Format
End of month — 60m, Exec presentation
Attendees
Exec team, Board (as needed), Key stakeholders
Content
Phase progress, budget, timeline, decisions
Key Metrics Dashboard: Acquisition, Engagement, Conversion, Retention, Revenue
Escalation Path
Technical Issues → Eng Lead | Infrastructure → DevOps | Timeline/Budget → PM | Critical → CTO/Exec
Documentation
Updates in Confluence • Metrics in Jira • Decisions in Decision Log

## Slide 15
Next Steps: Ready to Execute
Immediate Actions (This Week)
1
Secure Stakeholder Approval
Review plan, address concerns, obtain sign-off on timeline and budget
2
Finalize Team Assignments
Confirm all 12 team members, establish roles, schedule kickoff meeting
3
Prepare Infrastructure
AWS account setup, GitHub organization, communication tools configured
4
Create JIRA Project
Import all 10 tickets for Week 1 and 2, configure workflow and automations
Week 1 Kickoff (Monday)
1
Team Kickoff Meeting
Project overview, team introductions, roles and responsibilities clarification
2
Development Environment Setup
All developers clone repos, install dependencies, run local builds
3
GitHub Repository Initialization
Create repos, configure branch protection, set up team access
4
Daily Standups Begin
9:00 AM daily, 15 minutes, Engineering Lead facilitates
5
First Sprint Planning
Review JIRA tickets, estimate story points, assign tasks to developers
Success Criteria for Phase Completion
✓
All infrastructure operational with zero critical issues
✓
Backend running locally for all team members
✓
Database schema complete with 8 core tables
✓
Auth endpoints functional (register, login, OAuth)
✓
100% of planned story points completed
✓
Zero critical bugs in infrastructure or backend
✓
Development guide completed and tested
✓
Team ready to begin Phase 2 development
Phase Start
Monday, Week 1
Phase Duration
10 Business Days
Ready for Phase 2
Friday, Week 2

## Slide 16
Appendix: Detailed Task List — 10 JIRA Tickets
Week 1: Infrastructure Setup (39 Story Points)
PFORGE-101
5 pts
Initialize GitHub Repositories
Create 3 repos (backend, frontend, mobile), set up branch protection, team access, folder structure
PFORGE-102
8 pts
Set Up GitHub Actions CI/CD Pipeline
Configure workflows, automated testing, linting, code coverage, deployment pipeline
PFORGE-103
13 pts
Configure AWS Infrastructure
RDS PostgreSQL, ElastiCache Redis, S3 buckets, CloudFront, Lambda, VPC setup
PFORGE-104
8 pts
Set Up Monitoring, Logging & Error Tracking
Sentry integration, CloudWatch dashboards, ELK stack, alert rules, log aggregation
PFORGE-105
5 pts
Create Development Environment Guide
Setup instructions, troubleshooting, local development workflow, team onboarding
Week 2: Backend Architecture (47 Story Points)
PFORGE-106
8 pts
Initialize Express Backend
TypeScript setup, project structure, middleware stack, health check endpoint
PFORGE-107
13 pts
Design & Implement Database Schema
8 core tables, relationships, indexes, constraints, migrations, seed data
PFORGE-108
8 pts
Implement Authentication System
JWT tokens, OAuth 2.0 (Google, GitHub), password management, security measures
PFORGE-109
10 pts
Configure API Gateway & Middleware
Express router, versioning, logging, validation, rate limiting, CORS, response formats
PFORGE-110
8 pts
Scaffold Core Services
User, Project, Pack services with CRUD operations and business logic scaffolding
Budget Allocation Across Categories
Total Story Points
86 pts
Team Capacity
12 developers × 2 weeks
Phase Status
Ready to Execute

## Slide 17
Budget Summary: Detailed Allocation
Complete 10-day Foundation & Setup phase budget with cost efficiency metrics and ROI analysis
Budget Breakdown by Category
Category
Cost
% of Total
ROI Impact
Personnel (Engineering Lead + DevOps)
$120,000
61%
Enables 16-week development timeline with zero infrastructure blockers
AWS Infrastructure (RDS, ElastiCache, S3, Lambda)
$40,000
20%
Scalable foundation supporting 100K+ users at launch
Tools & Services (GitHub, Sentry, DataDog, Stripe)
$20,000
10%
Production-grade monitoring and error tracking from Day 1
Contingency (15% buffer for overruns)
$16,000
8%
Risk mitigation for unforeseen delays or scope changes
Total Phase 1 Budget
$196,000
100%
Foundation for $5M+ revenue potential
Cost per Story Point
$2,205
86 total story points across 10 JIRA tickets. Efficient allocation of resources.
Cost per Development Day
$19,600
10 working days with 2 senior engineers. Competitive rate for infrastructure setup.
Infrastructure Cost Efficiency
20%
AWS spend as percentage of total budget. Scalable, cost-effective cloud infrastructure.
Budget Status
Approved & Allocated
Expected ROI (Month 6)
$2M-5M Revenue
Payback Period
3-4 Months
Phase Completion
Day 10 (Friday, Week 2)

## Slide 18
Closing: Building the Future
PromptForge Foundation & Setup Phase — Ready for Execution
✓
Infrastructure Ready
Production-grade AWS, CI/CD, and monitoring ready from Day 1.
✓
Team Ready
12-person team assembled, roles defined, environments set.
✓
Timeline Clear
10-day plan with daily standups and weekly updates.
Our Vision
Build the world's smartest prompt pack system to empower entrepreneurs to create and scale digital products in weeks.
60 packs, 229 prompts, and intelligent composition — the Foundation phase lays the technical groundwork to make this real.
Next Steps to Launch
1
Stakeholder Approval
2
Team Kickoff
3
Infrastructure Setup
4
Phase 2 Launch
Phase Start Date
Monday, Week 1
Phase Duration
10 Business Days
Total Investment
$196,000
Expected ROI
$2M-5M (Month 6)